## Slide 1
TRD – Outer Chambers/modules
<Foliennummer>
Milestone | Date | 2021 | 2022 | 2023 | 2024 | 2025
Outer modules “5” |  |  |  |  |  | 
Module EDR | 10/19 |  |  |  |  | 
Module PRR + Start of prod. | 10/20 |  |  |  |  | 
Modules FOS + PRR follow up | 10/22 03/23 |  |  |  |  | 
Chambers all built (FAT) | 02/23 12/23 |  |  |  |  | 
Outer modules “3” |  |  |  |  |  | 
Start of prod. | 05/22 02/23 |  |  |  |  | 
FOS (PRR follow-up if needed) | 07/22 06/23 |  |  |  |  | 
All built (FAT) | 12/23 |  |  |  |  | 
Outer modules “7” |  |  |  |  |  | 
Production on-going
t.b.d.
Baseline 2023
Notes: <Foliennummer>

## Slide 2
TRD – Inner Chambers/Modules
<Foliennummer>
Milestone | Date | 2021 | 2022 | 2023 | 2024 | 2025
Inner modules (chamber + radiator + FEE) |  |  |  |  |  | 
TDR-Add internal review | 02/21 |  |  |  |  | 
TDR-Add submission | 05/21 |  |  |  |  | 
Inner modules “EDR” | 09/21 01/22 |  |  |  |  | 
TDR Addendum approval | 11/21 |  |  |  |  | 
Inner modules PRR | 02/22 |  |  |  |  | 
Start module production | 07/22 |  |  |  |  | 
Module FOS (batch of 10) | 06/23 |  |  |  |  | 
All chambers built | 06/24 |  |  |  |  | 
ECE 05/2021
ECE 11/2021
Moved  05/22 ? (should be discussed)
t.b.d.
Baseline 2023
Notes: <Foliennummer>

## Slide 3
TRD – Radiator box, Services, Mechanics
<Foliennummer>
Milestone | Date | 2021 | 2022 | 2023 | 2024 | 2025
Radiator box |  |  |  |  |  | 
Radiator EDR | 05/22 01/23 |  |  |  |  | 
Radiator PRR | 07/22 04/23 |  |  |  |  | 
Radiator FAT | 04/23 12/23 |  |  |  |  | 
Gas system |  |  |  |  |  | 
Gas CDR | 04/21 |  |  |  |  | 
Gas EDR | 07/22 04/23 |  |  |  |  | 
Gas PRR | 07/22 07/23 |  |  |  |  | 
Gas FAT | 11/23 04/23 |  |  |  |  | 
LV + HV systems |  |  |  |  |  | 
LV + HV EDR | 02/22 12/22 |  |  |  |  | 
LV + HV PRR | 04/22 12/22 |  |  |  |  | 
LV + HV FAT | 09/22 06/22 |  |  |  |  | 
Mechanics |  |  |  |  |  | 
Mainframe CDR | 10/20 |  |  |  |  | 
Support + Mainframe EDR | 05/22 01/23 |  |  |  |  | 
Support + Mainframe PRR | 09/22 06/23 |  |  |  |  | 
Support + Mainframe FAT | 03/23 12/23 |  |  |  |  | 
evaluation ongoing
decision on layer spacing needed
decision on layer spacing needed
being prepared
more time for preparation. funding?
can EDR and PRR be merged?
t.b.d.
Baseline 2023
Notes: <Foliennummer>

## Slide 4
TRD – ASIC, FEBs
<Foliennummer>
Milestone | Date | 2021 | 2022 | 2023 | 2024 | 2025
SPADIC ASIC + Front-End Boards |  |  |  |  |  | 
SPADIC 2.2 completed | 07/19 |  |  |  |  | 
SPADIC 2.3 submission | 12/20 |  |  |  |  | 
SPADIC 2.4 PRR | 05/22 03/23 |  |  |  |  | 
SPADIC 2.4 FAT | 03/23 09/23 |  |  |  |  | 
FEB CDR | 05/22 03/23 |  |  |  |  | 
FEB EDR | 11/22 09/23 |  |  |  |  | 
FEB PRR | 03/23 12/23 |  |  |  |  | 
FEB FOS, 1st batch sent | 06/23 02/24 |  |  |  |  | 
FEB FAT, all FEBs sent | 12/23 10/24 |  |  |  |  | 
SPADIC 2.3 evaluation on-going
t.b.d.
Baseline 2023