## Tabelle1
			comments
Outer chambers “5”	EDR	10/19
	SoP	02/23
	FOS	09/23	gain scan, tightness tests with FOS
	PRR	12/23
	FAT	01/25	production time for 2nd padplane badge expected large
Outer chambers “3” fund A	SoP	04/24	production time for padplane expected large
	FOS	10/24
	FAT	10/25
Outer chambers “3” fund B	SoP	05/25	funding unclear
	FOS	11/25
	FAT	10/26
Outer chambers “7”	SoP	01/26	required: funding to be granted in corresponding period
	FOS	12/26	preproduction of chamber components in parallel, but chamber closing just after “3”
	FAT	12/27
Buch in-kind	“CDR”	09/23	Depends on Addendum and FAIR/Romania interaction. The FEE building mainly depends on this document but also partially the common systems
	“PRR”	09/24
Inner chambers “1”	intRev, EDR	04/23	separate items Rad and FEE from inner chambers
	PRR	10/23
	FOS	04/24	Production of TRD-2D chambers can be started AFTER Addendum but BEFORE in-kind. Storage in Buch can also be accomodated until the full quota (44 chambers) is achieved.
	IMA	06/26	“intermediate approval”, 2 of 4 layers produced with internal acceptance
	FAT	06/27
Radiator	EDR	08/23	check with Lukas (1D) and Laura (2D) for mounting
	PRR	10/25	assuming: funding and production split as chambers (Romania/Germany)
	FAT	10/27	after detector install, before beam commissioning
Gas	CDR	04/21
	EDR	10/24	regulation line design can be confirmed
	FOS	10/25	first circulation line shown operational after potential corrections (EDR)
	PRR	01/26	funding lines 2–5 unclear, / assume installations in shaft 2026, but disentangle from “ready for install.”
	FAT	10/26
LV + HV	EDR	12/23	TRD2D: consider FEE as 12 V system, define DC/DC as part of the FEB design, funding LV cables, HV cables unclear, considered: FEASTs are purchsed by GSI
	PRR	01/26
	FAT	03/27	defined as “supplies in place”, distribution “to cave patch panel”
Mainframe + Support	CDR	10/20
	EDR	05/23
	PRR	09/23	earlier strongly desired, early purchasement ensures funding compatibility (Al)
	FAT	06/24	means: materials at storage
	Install (cave)	latest 06/26	please assign, funding for installation: money stored in team account
SPADIC ASIC	PRR	08/24	convergence to final version, fallback v2.2
	FAT	12/25
SPADIC FEB	CDR	08/24
	EDR	04/25
	PRR	12/25
	FOS	06/26
	FAT	03/27
FASP ASIC	PRR	09/26	New item. The FASP asic together with ADCs and Microsemi FPGA has to be tested for radiation hardness. This depends locally(Buch) on developments but also the external (GSI,etc) irradiators and/or eventual groups with mutual interests (e.g. STS). A contingency time of 2y wrt. The FEB CDR is considered.
	FAT	12/26	depends on the in-kind and PRR. We keep a 0.5y for installing ASIC on FEBs
FASP FEB	CDR	09/24	New item. The demonstrator version will be ready by 12/23. In order to test it during the mCBM 24 campaign and write the report we allocate a contingency time of 9 months.
	EDR	03/25	depends on CDR
	PRR	06/25
	FOS	01/26	should depend on the approval of the in-kind contract and not too far from the approval of the PRR.
	FAT	06/26

		general comments / - rename modules to chambers / (chamber = MWPC, / module = MWPC+Rad+FEE) / - further staging as, e.g., for hadrons only / on day 1 (w/o rad + gas) considerable? / proposed solution for financial risk in / “gas”.

CDR	Conceptual Design Review
EDR	Engineering Design Review
PRR	Production Readiness Review
SoP	Start of Production
FOS	First of Series
FAT	Factory Acceptance Test
(all produced)
f	”follow-up”