## Tabelle1
			comments
Buch in-kind	“CDR”	04/25	To be interpreted as “realistic draft”. The FEE costs have the highest influence (this is correlated to some problems seen in mCBM24). Also changes at the level of chamber pad-plane may influence the price.
	“PRR”	12/25	To be interpreted as “final version”. Should be done asap after the draft is approved (depends on interaction with the financial agency)
Inner chambers “1”	intRev, EDR	04/25	separate items Rad and FEE from inner chambers
	PRR	04/25	The design of the production chain was started in 2022. After 2 tryies we are still looking for the optimal solutions.
	FOS	06/25	The FOS TRD2D can be considered the output of the PRR. In house tests (w/o mCBM) should be enough. The target is anyhow to participate to mCBM25 from February.
	IMA	06/26	“intermediate approval”, 2 of 4 layers produced with internal acceptance
	FAT	06/27
Radiator	EDR	08/23	check with Lukas (1D) and Laura (2D) for mounting
	PRR	10/25	assuming: funding and production split as chambers (Romania/Germany)
	FAT	10/27	after detector install, before beam commissioning
Gas	CDR	04/21
	EDR	10/24	regulation line design can be confirmed
	FOS	10/25	first circulation line shown operational after potential corrections (EDR)
	PRR	01/26	funding lines 2–5 unclear, / assume installations in shaft 2026, but disentangle from “ready for install.”
	FAT	10/26
LV + HV	EDR	12/23	TRD2D: consider FEE as 12 V system, define DC/DC as part of the FEB design, funding LV cables, HV cables unclear, considered: FEASTs are purchsed by GSI
	PRR	01/26
	FAT	03/27	defined as “supplies in place”, distribution “to cave patch panel”
Mainframe + Support	CDR	10/20
	EDR	05/23
	PRR	09/23	earlier strongly desired, early purchasement ensures funding compatibility (Al)
	FAT	06/24	means: materials at storage
	Install (cave)	latest 06/26	please assign, funding for installation: money stored in team account
FASP ASIC	PRR	09/26	New item. The FASP asic together with ADCs and Microsemi FPGA has to be tested for radiation hardness. This depends locally(Buch) on developments but also the external (GSI,etc) irradiators and/or eventual groups with mutual interests (e.g. STS). A contingency time of 2y wrt. The FEB CDR is considered.
	FAT	12/26	depends on the in-kind and PRR. We keep a 0.5y for installing ASIC on FEBs
FASP FEB	CDR	09/24	New item. The demonstrator version will be ready by 12/23. In order to test it during the mCBM 24 campaign and write the report we allocate a contingency time of 9 months.
	EDR	04/25	depends on CDR
	PRR	06/25
	FOS	01/26	should depend on the approval of the in-kind contract and not too far from the approval of the PRR.
	FAT	06/26

		general comments / - rename modules to chambers / (chamber = MWPC, / module = MWPC+Rad+FEE) / - further staging as, e.g., for hadrons only / on day 1 (w/o rad + gas) considerable? / proposed solution for financial risk in / “gas”.

CDR	Conceptual Design Review
EDR	Engineering Design Review
PRR	Production Readiness Review
SoP	Start of Production
FOS	First of Series
FAT	Factory Acceptance Test
(all produced)
f	”follow-up”